## Call sheet
One sheet per shoot day. Send it the night before, usually as a PDF. Bump the version whenever anything changes.
CALL SHEET | [7 empty] | Production | [21 empty] | Version |  |  |  | v__ revised __:__
Date |  | Weekday, Month DD, YYYY | [9 empty] | Day |  |  | __ of __ |  |  |  |  | Director
Producer | [11 empty] | 1st AD | [12 empty] | 2nd AD
GENERAL CREW CALL | [9 empty] | Shooting call | [8 empty] | Lunch | [9 empty] | Est. wrap
[10 empty] | Breakfast | [8 empty] | Company move | [9 empty] | Sunrise / sunset
Weather |  |  |  | High __ / Low __ Rain __% Wind __ | [21 empty] | Forecast as of
Locations Full address, on-site contact, where crew parks
# | Location name and full address | [14 empty] | On-site contact | [8 empty] | Parking / basecamp / load-in
1
2
Nearest hospital (24-hr ER) | [5 empty] | Name, address, phone, drive time | [22 empty] | Emergency no.
Scene schedule In shooting order. Add meal and company-move rows where they happen.
Time |  |  | Sc |  | INT/EXT | Set / description | [14 empty] | D/N | Cast | [5 empty] | Pages |  |  | Loc |  |  |  | Notes
Pages in eighths (1 3/8 = one and three-eighths pages). Cast by ID number from the cast list. D = day, N = night.
Cast ID numbers match the scene schedule.
ID | Actor | [5 empty] | Character |  |  |  | Status |  |  | Pickup / O/T | [6 empty] | H/MU |  |  | On set |  |  |  |  | Remarks
Status: SW start work, W work, WF work finish, SWF start-work-finish (one-day role), H hold. O/T = own transport. H/MU = hair and makeup call.
Background and stand-ins | [8 empty] | Department notes | [17 empty] | General notes
Type, headcount, call, wardrobe, holding area | [8 empty] | Props, wardrobe, art, H/MU, camera, grip/electric, sound, vehicles
Crew Each person's call time. Double-check pre-calls (earlier than the general crew call).
Position |  |  |  |  | Name |  |  |  | Phone |  |  |  | Call |  |  |  | Position | [5 empty] | Name | [8 empty] | Phone |  |  |  | Call
Walkie channels | [5 empty] | Meals / catering | [9 empty] | Advance schedule (next day) | [16 empty] | Running late or lost?
Ch 1 Ch 2 Ch 3 | [15 empty] | Date, day count, tentative call, scenes | [16 empty] | Text:
Template by CREA — crea.website/en/tools/callsheet | [17 empty] | Free for personal and commercial use. Modify freely; no attribution required.

## Scene x cast breakdown
SCENE x CAST BREAKDOWN | [5 empty] | Who is in which scene. Not a Day Out of Days: a DOOD lists cast against shoot days, with status codes.
Project | [5 empty] | Script draft | [7 empty] | Date |  | Prepared by
Mark each scene with the cast ID number (or X). V = voice only / off screen. Pages in eighths (1 3/8). Fill in the shoot day once the schedule is set.
Sc | I/E | Set / location | D/N | Pages | Shoot day | Cast (ID and character) | [7 empty] | BG | Props | Wardrobe | SFX / equip. | Notes
[6 empty] | #1 | #2 | #3 | #4 | #5 | #6 | #7 | #8
[6 empty] | MARA | THEO | COOK
4 | INT | Diner - booth | N | 1.375 | Day 2 | Cast (ID and character) #1: 1; Cast (ID and character) #2: 2 |  | 3 bus tickets |  |  | Example row
5 | INT | Diner - counter | N | 0.75 | Day 2 | Cast (ID and character) #1: 1; Cast (ID and character) #2: V; Cast (ID and character) #3: 3 |  |  | Apron (3) |  | Example row
Scenes per cast member
Pages per cast member
Template by CREA — crea.website/en/tools/callsheet | [5 empty] | Cast (ID and character) #5: Free for personal and commercial use. Modify freely; no attribution required.

## Call sheet example
Example: the production, people, places and phone numbers are fictional (555-01xx numbers are reserved for fiction).
CALL SHEET | [8 empty] | Production |  |  |  | Night Bus to Kestrel Bay (short film) | [19 empty] | Version |  |  |  | v2, revised 9:40 PM Fri
Date |  | Saturday, November 14, 2026 | [11 empty] | Day |  |  | 2 of 3 |  |  |  |  | Director | [5 empty] | Sam Whitlock 555-0121
Producer |  | Dana Ellery 555-0112 | [11 empty] | 1st AD |  |  | Owen Hale 555-0134 | [10 empty] | 2nd AD |  |  |  | Priya Shah 555-0133
GENERAL CREW CALL | [5 empty] | 7:00 AM |  |  |  |  | Shooting call |  |  |  |  | 8:00 AM |  |  |  |  | Lunch |  |  |  | 1:00 PM | [6 empty] | Est. wrap | [7 empty] | 7:00 PM
[11 empty] | Breakfast |  |  |  |  | 6:30 AM |  |  |  |  | Company move |  |  |  | 3:30 PM | [6 empty] | Sunrise / sunset | [7 empty] | 6:41 AM / 4:52 PM
Weather |  |  |  | Partly cloudy. High 61°F / Low 48°F. Rain 20%. Wind 8 mph. | [24 empty] | Forecast as of | [8 empty] | 6:00 PM Fri
Locations Full address, on-site contact, where crew parks
# | Location name and full address | [16 empty] | On-site contact | [9 empty] | Parking / basecamp / load-in
1 | Hollis Street Diner, 214 Hollis St, Kestrel Bay | [16 empty] | Ana Ruiz 555-0147 | [9 empty] | Crew lot behind the laundromat, enter from Pine Ave. Basecamp: church lot, 230 Pine Ave
2 | Bus shelter, Hollis St and 3rd Ave | [16 empty] | Dana Ellery (producer) | [9 empty] | Street parking on 3rd Ave only.
Nearest hospital (24-hr ER) | [6 empty] | Kestrel Bay General Hospital, 24-hr ER, 1200 Harbor Rd, 555-0190, 8 min drive | [24 empty] | Emergency no. | [6 empty] | 911
Scene schedule In shooting order. Add meal and company-move rows where they happen.
Time |  |  | Sc |  | INT/EXT |  | Set / description | [15 empty] | D/N | Cast | [6 empty] | Pages |  |  | Loc |  |  |  | Notes
8:00 AM |  |  | 4 |  | INT |  | DINER - BOOTH. Mara asks Theo for the bus fare | [15 empty] | N | 1, 2 | [6 empty] | 1 3/8 |  |  | 1 |  |  |  | Windows tented
9:45 AM |  |  | 5 |  | INT |  | DINER - COUNTER. The cook won't make change | [15 empty] | N | 1, 3 | [6 empty] | 6/8 |  |  | 1
11:00 AM |  |  | 6 |  | INT |  | DINER - BACK HALL. Mara overhears a call | [15 empty] | N | 1 | [6 empty] | 5/8 |  |  | 1 |  |  |  | Closed set
1:00 PM |  |  | LUNCH - 30 min, catered at basecamp
1:30 PM |  |  | 8 |  | INT |  | DINER - BOOTH. Mara and Theo split a pie | [15 empty] | N | 1, 2 | [6 empty] | 1 2/8 |  |  | 1 |  |  |  | BG x6
3:30 PM |  |  | COMPANY MOVE to LOC 2 (10 min drive)
4:15 PM |  |  | 10 |  | EXT |  | BUS SHELTER. The bus pulls away without them | [15 empty] | D | 1, 2 | [6 empty] | 3/8 |  |  | 2 |  |  |  | Dusk. Before 4:52 PM
5:30 PM |  |  | 12 |  | EXT |  | BUS SHELTER. Theo waves down the night bus | [15 empty] | N | 1, 2 | [6 empty] | 6/8 |  |  | 2 |  |  |  | Gimbal. Hi-vis vests
Pages in eighths (1 3/8 = one and three-eighths pages). Cast by ID number from the cast list. D = day, N = night.
Cast ID numbers match the scene schedule.
ID | Actor | [6 empty] | Character |  |  |  | Status |  |  |  | Pickup / O/T | [6 empty] | H/MU |  |  |  | On set |  |  |  |  | Remarks
1 | Lena Ortiz | [6 empty] | MARA |  |  |  | W |  |  |  | O/T | [6 empty] | 7:00 AM |  |  |  | 7:45 AM |  |  |  |  | Bring own black boots
2 | Jonah Reyes | [6 empty] | THEO |  |  |  | W |  |  |  | 6:30 AM, 41 Elm Ct | [6 empty] | 7:15 AM |  |  |  | 7:50 AM
3 | Ruth Abara | [6 empty] | COOK |  |  |  | SWF |  |  |  | O/T | [6 empty] | 8:45 AM |  |  |  | 9:30 AM |  |  |  |  | One-day role
Status: SW start work, W work, WF work finish, SWF start-work-finish (one-day role), H hold. O/T = own transport. H/MU = hair and makeup call.
Background and stand-ins | [9 empty] | Department notes | [19 empty] | General notes
Diner patrons x6 for Sc 8. Call 12:30 PM. Fall casual, no logos. Holding: church hall. | [9 empty] | Props: 3 bus tickets (hero + 2 spares), coins. Grip: tent diner windows for Sc 4-8. Sound: fridge off during takes. Camera: gimbal for Sc 12. | [19 empty] | Closed set for Sc 6. Talent: bring signed release forms. No drones without the producer's OK.
Crew Each person's call time. Double-check pre-calls (earlier than the general crew call).
Position |  |  |  |  | Name |  |  |  |  | Phone |  |  |  |  | Call |  |  |  | Position | [6 empty] | Name | [8 empty] | Phone | [5 empty] | Call
Director |  |  |  |  | Sam Whitlock |  |  |  |  | 555-0121 |  |  |  |  | 7:00 AM |  |  |  | 1st AC | [6 empty] | Ben Okafor | [8 empty] | 555-0143 | [5 empty] | 6:45 AM
Producer |  |  |  |  | Dana Ellery |  |  |  |  | 555-0112 |  |  |  |  | 6:30 AM |  |  |  | Gaffer | [6 empty] | Rui Tanaka | [8 empty] | 555-0158 | [5 empty] | 6:30 AM
1st AD |  |  |  |  | Owen Hale |  |  |  |  | 555-0134 |  |  |  |  | 6:45 AM |  |  |  | Sound mixer | [6 empty] | Cal Brandt | [8 empty] | 555-0162 | [5 empty] | 7:00 AM
2nd AD |  |  |  |  | Priya Shah |  |  |  |  | 555-0133 |  |  |  |  | 6:30 AM |  |  |  | Prod. designer | [6 empty] | Ines Varga | [8 empty] | 555-0170 | [5 empty] | 6:30 AM
DP |  |  |  |  | Mika Laine |  |  |  |  | 555-0141 |  |  |  |  | 7:00 AM |  |  |  | H/MU, first aid | [6 empty] | Jo Kim | [8 empty] | 555-0175 | [5 empty] | 6:45 AM
Walkie channels | [6 empty] | Meals / catering | [10 empty] | Advance schedule (next day) | [17 empty] | Running late or lost?
Ch 1 Production Ch 2 Private Ch 3 Transport | [6 empty] | Breakfast 6:30 AM at basecamp Lunch 1:00 PM, catered Vegan x2, gluten-free x1 | [10 empty] | Sun, Nov 15 - Day 3 of 3 Tentative crew call 3:00 PM Sc 9, 11 EXT. BUS STOP - N (LOC 2) | [17 empty] | Text Priya (2nd AD) 555-0133
Template by CREA — crea.website/en/tools/callsheet | [19 empty] | Free for personal and commercial use. Modify freely; no attribution required.